## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | term-swen-261-06-1a goodvibes
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | SB, KB, AM, JR; 03/14/2024
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | SB, KB, AM, JR; 03/14/2024
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | SB, KB, AM, JR; 03/14/2024
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | SB, KB, AM, JR; 03/14/2024
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | SB, KB, AM, JR; 03/14/2024
As an owner, I want the users to log in using a unique username, so that everyone can easily log in and make purchases. | Given that the Owner writes admin, it directs them to the admin page | Pass | SB, KB, AM, JR; 03/16/2024
| Given that the Customer logs in with whatever username, it directs them to the Customer Homepage | Pass | SB, KB, AM, JR; 03/16/2024
| Given that the email does not exist, the user is notified of that either via a pop-up or a field next to the email field indicating that the account does not exist | Pass | SB, KB, AM, JR; 03/16/2024
As an owner, I want to add new products to the inventory, so that the business always stays up to date with recent trends. | Given an admin user is logged in when viewing the product database then they should be able to add a puzzle to the database given some information. | Pass | SB, KB, AM, JR; 03/16/2024
| Given a user is looking at the available puzzles when an admin adds a new one then they should be able to view the new puzzle on their end. | Pass | SB, KB, AM, JR; 03/16/2024
As an owner, I want to edit the data of any product in the inventory, so that the presentation to the customer is as perfect as possible. | Given the owner updates product information when a customer searches for the product then, the json file should reflect the changes and the new information should be displayed. | Pass | SB, KB, AM, JR; 03/16/2024
| Given that the JSON file changes, the cached data should also automatically change and should not require the user to manually clear the browser cache | Pass | SB, KB, AM, JR; 03/16/2024
As an owner, I want to remove an inventory item, so that the customers do not see out of stock or gone products in the website. | Given the admin removes a product when they look at the inventory then they expect that the product no longer exists. | Pass | SB, KB, AM, JR; 03/16/2024
| Given the user searches available products when the owner removes an item then the user should not see it. | Pass | SB, KB, AM, JR; 03/16/2024
As a buyer, I want to add products I like to cart, so that I can easily find them should I choose to make a purchase later. | Given a user presses add product to cart, the product gets added to Cart.json. A prompt is shown in the page indicating that the product is added to the cart | Pass | SB, KB, AM, JR; 03/17/2024
| Given the same product is attempted to be added to the cart, update and increment the quantity field of the existing entry | Pass | SB, KB, AM, JR; 03/17/2024
As a buyer, I want to remove products I don’t want from cart, so that the cart doesn’t have unnecessary information in the cart. | Given a user presses remove product from cart, the product gets deleted from Cart.json. A prompt is shown in the page indicating that the product is removed from the cart. | Pass | SB, KB, AM, JR; 03/17/2024
As a buyer, I want to be able to search for a specific product by its code or category so that I can find exactly what I need easily. | Given that the user searches for the name and presses enter, a request is sent to the REST API with that name as a parameter | Pass | SB, KB, AM, JR; 03/15/2024
| Given that the API gets the request and returns the list, the product page now correctly displays the list of the fetched puzzles that contain the string in the name | Pass | SB, KB, AM, JR; 03/15/2024
As a buyer, I want checkout to offer different payment methods, so that I can make the purchase as quickly as possible. | Given the user checks out, the product gets added to their "purchased list" and purchase count increments by 1
Given the checkout fails, the user is notified through a toast/top bar
As a User, I want to be able to write gift note-cards and send the puzzle to an email address of my choice, so that I can make the day of my puzzle-lover friends. | Given a gifting menu when select the option at checkout then I expect to be able to send the puzzle as a gift to the address listed.
As a User, I want to be able to generate a puzzle from an image, so that I can have the item that I exactly want. | Given an image when I upload it to a designated section then I see a custom puzzle made from that image.
Given that the user submits a URL of the image, we do not save it locally to the folder yet
As an owner, I want to offer the option to save payment information, so that there is no need for the users to spend time on it more than once. | Given that a required information field is not filled, the page does not allow to complete payment
Given the user provides the correct information, they can see their payment info in a seperate menu called `payment`
Given that the payment is not validated, hints are shown to display where mistakes might be